## Budget
BUDGET BREAKDOWN PER ACTIVITIES/ITEMS IN 2022/23 FY |  |  |  |  | BUDGET DETAILS |  |  | PROCUREMENT & EXPENDITURE STATUS
No | Activity | Quantity | Unit(s) | R/Unit(s) | Available | Required | Shortfall | Pending | Advert | Commit | Spent | Total
1 | Capacity Building/Training and Awareness Campaigns | 93 | Each | 1700 | 168000 | 158100 | 9900 | 117300 | 160808 |  |  | 278108
2 | Catering Services | 9 | Event |  | 32500 |  | 32500 |  |  |  | 28965.63 | 28965.63
3 | Protective Clothing | 93 | Each | 1663.26 | 38000 | 154683.18 | -116683.18 |  |  |  |  | 0
4 | Farm/Gardeng Suppplies: Implements/Other Materials | 91 | Each | 321.0037 | 51500 | 146684.86 | -95184.86 |  | 51405 |  |  | 51405
5 | Inv Farm Sup: Seeds&Sedlin/Compost | 132 | Each | 725.94 | 58921 | 100298.88 | -41377.88 |  |  |  |  | 0
6 | Installation of RWH systems | 24 | Each | 18768.8246 | 112000 | 450451.7892 | -338451.7892 |  |  |  |  | 0
7 | [6 empty] | 0 |  |  |  |  | 0
Total |  |  |  |  | 460921 | 1010218.7092 | -549297.7092 | 117300 | 212213 | 0 | 28965.63 | 358478.63

## Schools 2022-23
ACTIVITY PLAN AND RESOURCE REQUIREMENTS FOR 2022-23 AGRO-ECO SCHOOLS
cid:image001.png@01D62EBB.91C24B80
NO | NAME OF SCHOOL / CA GARDEN | LOCAL MUNICIPALITY | LOCALITY/AREA | CATERGORY / CLASSIFICATION | NO OF LEARNERS | GRADE/S | ACTIVITY |  |  |  | RESOURCES REQUIRED FOR 2022/23 BUDGET
[7 empty] | GARDEN | GARDEN SIZE (m2) | CAREER AWARENESS | TRAINING / CAPACITY BUILDING | Protective Clothing (& quantities) | Tools/Implements | Production Inputs | Infrastructure / Facilities | Other (Specify) : Training/C-building
1 | Msobomvu Full Service School | Blue Crane Route | Cookhouse | MEC Adopted | 20 | Gr 4-7 | Vegetables | 5000 |  | C.A; Permaculture | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Litmus and filter paper, Solar system (Mobile), Maths 2D 3D shapes, Iodine, Kitchen scale, stopwatch, telescope | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Receieved in 2019/20
2 | Johnson Nqonqoza Senior Secondary | Blue Crane Route | Somerset East | MEC Adopted | 40 | Gr 9,10,11 | Vegetables | 100 | 21/09/2022 | C.A; Permaculture | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2x50m hose pipes,3xgarden spades, 3xfolk spades, 2x wheelbarrows, 3xwatering cans, 3xsteel rakes, 3xmeasuring jugs, 3xhand folks, 3xhand spades, 2xprunning saws | Seeds: Spinach; beetroot, peppers, butternut and 16x Bags of compost | 2x5000L Jojo Tanks with stand, gutters and connections to the garden, 1xwater pump
3 | Coldstream PS | Koukamma LM | Coldstream | MEC Adopted | 10 | Gr 7 - 9 | Vegetables | 36 | 05/10/2022 (JLC Awareness) | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x5000L Jojo Tanks with stand, gutters and connections to the garden | DRDAR and DALRRD LandCare competitions
4 | Gustav PS | Koukamma LM | Eersterivier | MEC Adopted | 10 | Gr 5 - 6 | Vegetables | 920 | 05/10/2022 (JLC Awareness) | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | N/A | DRDAR and DALRRD LandCare competitions
5 | Joubertina Sec. | Koukamma LM | Joubertina | MEC Adopted | 10 | Gr 7 - 9 | Vegetables |  | 05/10/2022 (JLC Awareness) | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x5000L Jojo Tanks with stand, gutters and connections to the garden | DRDAR and DALRRD LandCare competitions
6 | Iqhayiya Lethu S.S. | Koukamma LM | Kareedouw | MEC Adopted | 10 | Gr 8 - 12 | Vegetables | 1 28 | 17/08/2022 | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 3x 5000L jojo Tanks with stands Gutters and connections to the garden | DRDAR and DALRRD LandCare competitions
7 | Louterwater PS | Koukamma LM | Louterwater | MEC Adopted | 10 | Gr 7 - 9 | Vegetables | 4000 | 05/10/2022 (JLC Awareness) | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | N/A | DRDAR and DALRRD LandCare competitions
8 | Misgund PS | Koukamma LM | Misgund | MEC Adopted | 10 | Gr 7 - 9 | Vegetables |  | 05/10/2022 (JLC Awareness) | CA Principles/ Technologies; Vermi-composting; Vegetables/Crop Production | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 2xwheelbarrow, 6xwatering cans, 6xfolk spades, 2xhand hoes, 6x seedling trays, 6xspades | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Renovations of water harvesting infrastructure | DRDAR and DALRRD LandCare competitions
9 | Nombulelo Senior Secondary School | Makan LM | Makhanda | MEC Adopted | 16 | 9,10,11 | Vegetables |  | 12/08/2022 | Vermi-composting: 09/2022 Mulching technique: 09/2022 | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Fencing & 2 gates, 1x wheelbarrow, 5xfork spades, 2x50m hose pipes, Grass cutter machine (petrol), Seedlings, 5x garden spades, 2xRecycle bins, 5x prunning shears | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x5000L Jojo Tanks with stand, gutters and connections to the garden | Chemical use and Herbicide handlind; C.A; Permaculture
10 | Ikamvalesizwe Combined School | Ndlambe LM | Kenton On Sea | MEC Adopted | 57 | Gr 10-12 | Vegetables |  | 05/08/2022 | Vermi-composting: 09/2022 Mulching technique: 09/2022 | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xwheelbarrow, 15xwatering cans, 15xfolk spades, 15xhand hoes, 6x seedling trays, 15xspades | Seeds: Spinach; cabbage, carrot,onions and 10x Bags of compost | 4X5000L Jojo Tanks with stands Gutters and connections to the Garden
11 | Mzingisi Primary School | Kouga LM | Humansdorp | Agro-Eco School | 20 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 5x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Received in 2020/21 | C.A; Permaculture
12 | Archie Mbolekwa Primary | Makan LM | Makhanda | Agro-Eco School | 20 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Received in 2018/19 | Seeds: Spinach; beetroot, peppers, butternut | Received in 2018/19 | C.A
13 | Fikizolo Primary School | Makan LM | Makhanda | Agro-Eco School | 20 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Received in 2018/19 | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Received in 2018/19 | C.A
14 | Kutlhiso Daniels Secondary school | Makan LM | Makhanda | Agro-Eco School | 15 | Gr8,9 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 1x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x5000L Jojo Tanks with stand, gutters and connections to the garden | C.A; Permaculture
15 | Ntsika Secondary School | Makan LM | Makhanda | Agro-Eco School | 50 | Gr8,9 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 5x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Water is in abundance at this school as Gift of the givers supplied two boreholes | C.A; Permaculture
16 | Samuel Ntlebi Primary School | Makan LM | Makhanda | Agro-Eco School | None |  | Vegetables |  |  |  |  | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 1x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 1x5000L Jojo tank with stand, gutters connected to the tank | Permaculture
17 | Samuel Ntsiko Public Primary | Makan LM | Makhanda | Agro-Eco School | 10 | Gr 2,4,5 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 3x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x 5000L jojo Tanks with stands, Gutters and connections to the garden | Permaculture
18 | Zuney Intermediate School | Ndlambe LM | Alexandria (Along R72 road) | Agro-Eco School | 15 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Received in 2018/19 | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Received in 2018/19 | C.A
19 | Ukhanyo Secondary School | Ndlambe LM | Alexandria (Nonkqubela location) | Agro-Eco School | 15 | Gr 5 -9 | Vegetables |  |  | Vermi-composting: 09/2022 Mulching technique: 09/2022 | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 3x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x 5000L jojo Tanks with stands Gutters and connections to the garden | Vermi-composting: 09/2022 Mulching technique: 09/2022
20 | Klipfontein Primary School | Ndlambe LM | BushmansRiverMouth | Agro-Eco School | 15 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x2L Watering Cans, 5x Spades, 5x Folk spades, 3x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | 2x 5000L jojo Tanks with Gutters and connections to the garden | C.A
21 | A.V Bukani Primary School | Sundays Rive Valley | Addo | Agro-Eco School | 20 | Gr 4-7 | Vegetables |  |  |  | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | Received in 2020/21 | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | Received in 2020/21 | C.A; Permaculture
22 | Bhongweni primary school | Ndlambe LM | Alexandria (Nonkqubela location) | Agro-Eco School | 15 | Gr 4-7 | Vegetables |  |  | CA Principles/ Technologies | Gumboots, Hand Gloves, Plastic Aprons, Sun Hats, Work Coats | 3xWheelbarrow, 5x10L Watering Cans, 5x Spades, 5x Folk spades, 3x 50m hose pipes, 3x rakes | Seeds: Spinach; beetroot, peppers, butternut and 10x Bags of compost | There is enough water tanks at Bhongweni | C.A

## Pupils List
LEARNERS PARTICPATING IN JUNIOR LANDCARE GARDEN ACTIVITIES IN 2022/23 FY
SIZES FOR REQUIRED PPE's
NO | SURNAME | FIRST NAMES | ID NUMBER | DOB | GENDER | AGE | GRADE | Work Coat / Apron | Saftey shoes /Gumboots | Sun hat | Hand gloves | SCHOOL NAME | LOCATION | MUNICIPALITY
1 | BASHI | ANESIPHO | 1008070235081 | 2010-08-07 | F | 13 | 6 | 34 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
3 | BOTHA | LINDOKUHLE | 1002261226083 | 2010-02-26 | F | 13 | 6 | 34 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
4 | CHIMATA | NICHOLE | 15-1612H5-N15 | 2014-12-31 | F | 9 | 6 | 34 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
5 | DEMELE | LELETHU | 1003300618082 | 2010-03-30 | F | 13 | 6 | 32 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
6 | DYALOYI | ASOMELEZE | 1009040257081 | 2010-09-04 | F | 13 | 6 | 30 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
7 | DYONGMAN | ZIZO | 1010240142081 | 2010-10-24 | F | 13 | 6 | 32 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
8 | FREDDIE | AVETHANDWA | 1009051258085 | 2010-09-05 | F | 13 | 6 | 34 | 2 | M | M | Fikizolo Primary School | Makhanda | Makana
9 | JODAY | ASESIHLE | 1002140423083 | 2010-02-14 | F | 13 | 6 | 32 | 2 | M | M | Fikizolo Primary School | Makhanda | Makana
10 | KOLONI | SIYAMBONGA | 0811175844083 | 2008-11-17 | M | 15 | 6 | 36 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
11 | KONDILE | SIYAMTHANDA | 1006210553083 | 2010-06-21 | F | 13 | 6 | 28 | 12 | M | M | Fikizolo Primary School | Makhanda | Makana
12 | KRISTJAN | NOMAPHELO | 1003021303089 | 2010-03-02 | F | 13 | 6 | 38 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
13 | KULATI | AMYOLI | 1001035252086 | 2010-01-03 | M | 13 | 6 | 34 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
14 | MADLINGOZI | LIYEMA | 1003026581085 | 2010-03-02 | M | 13 | 6 | 30 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
15 | MAGWAXAZA | AMILA | 1002100471080 | 2010-02-10 | F | 13 | 6 | 36 | 6 | M | M | Fikizolo Primary School | Makhanda | Makana
16 | MAKAPELA | XABISO | 0907165317088 | 2009-07-16 | M | 14 | 6 | 32 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
17 | MAKASI | AQHAMA | 0809150401085 | 2008-09-15 | F | 15 | 6 | 34 | 5 | M | M | Fikizolo Primary School | Makhanda | Makana
18 | MANGA | ESETHU | 0905195461082 | 2009-05-19 | M | 14 | 6 | 34 | 5 | M | M | Fikizolo Primary School | Makhanda | Makana
19 | MANTJIES | SIPHESIHLE | 1007125571087 | 2010-07-12 | M | 13 | 6 | 34 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
20 | MPIYANE | NOAH | 0910236225082 | 2009-10-23 | M | 14 | 6 | 36 | 6 | M | M | Fikizolo Primary School | Makhanda | Makana
21 | NCESE | SIYAVUYA | 0905085719086 | 2009-05-08 | M | 14 | 6 | 32 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
22 | NGXONGO | EMIHLE | 1006150287080 | 2010-06-15 | F | 13 | 6 | 32 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
23 | NONYATI | UYAKHA | 1102156047089 | 2011-02-15 | M | 12 | 6 | 32 | 2 | M | M | Fikizolo Primary School | Makhanda | Makana
24 | NONZIMBA | APHEPHILE | 0801275631084 | 2008-01-27 | M | 15 | 6 | 34 | 6 | M | M | Fikizolo Primary School | Makhanda | Makana
25 | PATSHA | SONGENATHI | 1009300314085 | 2010-09-30 | F | 13 | 6 | 34 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
26 | RALO | ENDINAKO | 1007095386086 | 2010-07-09 | M | 13 | 6 | 32 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
27 | SOLOLO | LINAMANDLA | 1008055132080 | 2010-08-05 | M | 13 | 6 | 32 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
28 | VAYO | ELETHU | 0909080110085 | 2009-09-08 | F | 14 | 6 | 34 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
29 | VROEGMAN | IVIWE | 0908150597087 | 2009-08-15 | F | 14 | 6 | 32 | 3 | M | M | Fikizolo Primary School | Makhanda | Makana
30 | YAKA | THIMNA | 1004170269089 | 2010-04-17 | F | 13 | 6 | 34 | 4 | M | M | Fikizolo Primary School | Makhanda | Makana
2 | BENNET | KHANYISA | 1002055296086 | 2010-02-05 | M | 13 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
31 | BOMALI | THATHO | 1010216135085 | 2010-10-21 | M | 13 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
32 | BRANDER | OYAMA | 1102046244086 | 2011-02-04 | M | 12 | 6 | M | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
33 | BRUINTJIES | THANDOLWETHU | 1104106145088 | 2011-04-10 | M | 12 | 5 | S | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
34 | DAVIDS | MICHELLE | 0811111185088 | 2008-11-11 | F | 15 | 6 | M | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
35 | DINGILE | YANDISA | 0906276382080 | 2009-06-27 | M | 14 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
36 | DYANTYI | AYABONGA | 0912195788084 | 2009-12-19 | M | 14 | 5 | S | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
37 | DYASI | OYIMVANA | 1104100406080 | 2011-04-10 | F | 12 | 5 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
38 | DYASI | SINOVUYO | 1006090792082 | 2010-06-09 | F | 13 | 6 | M | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
39 | FOLOLO | CHULUMANCO | 1205250977083 | 2012-05-25 | F | 11 | 5 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
40 | FOZA | AKHANYA | 1010241122082 | 2010-10-24 | F | 13 | 5 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
41 | GCUME | SIBONGAKONKE | 1010155541087 | 2010-10-15 | M | 13 | 5 | M | 7 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
42 | GQOZO | QHAMA | 1002165820080 | 2010-02-16 | M | 13 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
43 | JACOBS | ANELITHA | 09030551130081 | 2009-03-05 | M | 14 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
44 | KATO | ANDISIWE | 1111010271082 | 2011-11-01 | F | 12 | 5 | M | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
45 | KHETSHIWE | APHELELE | 0911255524082 | 2009-11-25 | M | 14 | 6 | M | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
46 | KINANA | LITHABISE | 1107135500082 | 2011-07-13 | M | 12 | 5 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
47 | KLAAS | ZINTLE | 1102011536086 | 2011-02-01 | F | 12 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
48 | LUBAXA | MINENTLE | 1111020152082 | 2011-11-02 | F | 12 | 5 | M | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
49 | MABELE | SANGENATHI | 1011071091088 | 2010-11-07 | F | 13 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
50 | MABINDISA | LINDOKUHLE | 0906136289087 | 2009-06-13 | M | 14 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
51 | MAJIKAZANA | AMTHANDILE | 0902235687081 | 2009-02-23 | M | 14 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
52 | MAJOLA | LIYAKHANYA | 1007191343080 | 2010-07-19 | F | 13 | 6 | M | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
53 | MAKONZA | SIYAMTHANDA | 0809241446081 | 2008-09-24 | F | 15 | 6 | L | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
54 | MAZALENI | BAVUYISE | 0909036109082 | 2009-09-03 | M | 14 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
55 | MENE | ANOTHANDO | 1103041522088 | 2011-03-04 | F | 12 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
56 | MGWANQA | ZIMKHITHA | 1008081242085 | 2010-08-08 | F | 13 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
57 | MQHIKI | ANELISIWE | 0808260172081 | 2008-08-26 | F | 15 | 6 | M | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
58 | MXADANA | UYATHANDWA | 1108300242088 | 2011-08-30 | F | 12 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
59 | NDLAZI | SIPHOKUHLE | 1101231137089 | 2011-01-23 | F | 12 | 6 | M | 5 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
60 | NDYAMARHA | IMANGE | 1104236303086 | 2011-04-23 | M | 12 | 5 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
61 | NKAYI | ZUBENATHI | 1201110266080 | 2012-01-11 | F | 11 | 5 | S | 1 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
62 | PILISO | BAXOLISE | 1008166256083 | 2010-08-16 | M | 13 | 6 | S | 2 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
63 | SIAS | AYABONGA | 0710196361087 | 2007-10-19 | M | 16 | 6 | L | 8 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
64 | SIKWEBU | ZENANDE | 1110270731082 | 2011-10-27 | F | 12 | 5 | S | 3 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
65 | SIZANI | SIYAMTHANDA | 0905276395084 | 2009-05-27 | M | 14 | 6 | L | 6 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
66 | THONGA | LINDISIPHO | 1109160832083 | 2011-09-16 | F | 12 | 5 | S | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
67 | THONGA | LUKHOLOLWETHU | 1107226140087 | 2011-07-22 | M | 12 | 5 | S | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
68 | VAZI | BUNCWANE | 0905230672081 | 2009-05-23 | F | 14 | 6 | L | 6 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
69 | VUNATHI | ASOMELEZE | 1203165461097 | 2012-03-16 | M | 11 | 5 | S | 4 | ONE SIZE | S | Msobomvu Full Service Schl | Cookhouse | Blue Crane Route
70 | BONANI | SIYAMTHANDA | 0807185418082 | 2008-07-18 | M | 15 | 6 | 14-15 YEARS | 6 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
71 | CHIKUTA | MELLISA | 29-2058203L38 | 2028-10-05 | M | -5 | 6 | 12-13 YEARS | 4 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
72 | GOJELA | LINOVUYO | 1001196060082 | 2010-01-19 | M | 13 | 6 | 12-13 YEARS | 5 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
73 | HLUNGULU | ZINGCE | 1011285616088 | 2010-11-28 | M | 13 | 6 | 12-13 YEARS | 3 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
74 | JALI | ANELE | 1011025235082 | 2010-11-02 | M | 13 | 4 | 13-14 YEARS | 6 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
75 | MAGONGO | APHIWE | 0808035637083 | 2008-08-03 | M | 15 | 4 | 13-14 YEARS | 5 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
76 | MATUTU | YANGA | 0902205491080 | 2009-02-20 | M | 14 | 3 | 13-14 YEARS | 6 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
77 | SLANGE | KHANYISILE | 1001251584089 | 2010-01-25 | F | 13 | 6 | 13-14 YEARS | 3 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
78 | WITBOOI | ABONGILE | 0812086837083 | 2008-12-08 | M | 15 | 5 | 14-15 YEARS | 6 | M | M | Samuel Ntsiko Public Primary | Makhanda | Makana
79 | ZONDANI | INAM | 1402116351081 | 2014-02-11 | M | 9 | 2 | 8-9 YEARS | 1 | S | S | Samuel Ntsiko Public Primary | Makhanda | Makana
80 | ADAM | ZINZI | 0804290492086 | 2008-04-29 | F | 15 | 9 | M | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
81 | DIAMOND | ZANDILE | 0704230609080 | 2007-04-23 | F | 16 | 9 | S | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
82 | DYAKALA | AWONKE | 0603115405087 | 2006-03-11 | M | 17 | 9 | M | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
83 | KRANZ | LIYEMA | 062145536085 | 2007-10-15 | M | 16 | 9 | M | 8 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
84 | MADOLO | AMBESIWE | 0712051007086 | 2007-12-05 | F | 16 | 9 | L | 8 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
85 | MOODY | REEJ | 0412085999081 | 2004-12-08 | M | 19 | 9 | M | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
86 | MSIPA | LUBABALO | 0504035606087 | 2005-04-03 | M | 18 | 9 | M | 8 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
87 | NCAPHAYI | ZUSAKHE | 0608200767085 | 2006-08-20 | F | 17 | 9 | S | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
88 | NCWADI | EMIHLE | 0705160541086 | 2007-05-16 | F | 16 | 9 | S | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
89 | NKO | INGANATHI | 0803040186089 | 2008-03-04 | F | 15 | 9 | M | 8 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
90 | PAMA | APHELELE | 0505065548081 | 2005-05-06 | M | 18 | 9 | S | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
91 | PAMA | SIYAVUYA | 0404085443087 | 2004-04-08 | M | 19 | 9 | S | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
92 | RALO | ASEMAHLE | 0612221029087 | 2006-12-22 | F | 17 | 9 | M | 7 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
93 | RALO | SISIPHO | 0610081232080 | 2006-10-08 | F | 17 | 9 | L | 8 | M | M | Kutlhiso Daniels Secondary Schl | Makhanda | Makana
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
Formulas:
DOB = IF([ID NUMBER]="","",IF(VALUE(LEFT([ID NUMBER],2))<40,DATE(100+VALUE(LEFT([ID NUMBER],2)),VALUE(MID([ID NUMBER],3,2)),VALUE(MID([ID NUMBER],5,2))),DATE(VALUE(LEFT([ID NUMBER],2)),VALUE(MID([ID NUMBER],3,2)),VALUE(MID([ID NUMBER],5,2)))))

## ProtectiveClothing
LEARNERS PARTICPATING IN JUNIOR LANDCARE GARDEN ACTIVITIES IN 2022/23 FY
ESTIMATED COSTS
NO | SCHOOL NAME | LOCAL MUNICIPALITY | LOCALITY/AREA | CATERGORY / CLASSIFICATION | NO OF LEARNERS | Work Coat / Jacket | Plastic Apron | Saftey shoes /Gumboots | Sun hat | Hand gloves | Total Costs
[5 empty] | 1663.26 | 387.6 | 161.88 | 929.1 | 129.96 | 54.72 | (Rands)
1 | Msobomvu Full Service Schl | Blue Crane Route | Cookhouse | MEC Adopted | 40 | 15504 | 6475.2 | 37164 | 5198.4 | 2188.8 | 66530.4
2 | Johnson Nqonqoza Senior Secondary | Blue Crane Route | Somerset East | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Coldstream PS | Koukamma LM | Coldstream | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gustav PS | Koukamma LM | Eersterivier | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Joubertina Sec. | Koukamma LM | Joubertina | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Iqhayiya Lethu S.S. | Koukamma LM | Kareedouw | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Louterwater PS | Koukamma LM | Louterwater | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Misgund PS | Koukamma LM | Misgund | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Nombulelo Senior Secondary School | Makan LM | Makhanda | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Ikamvalesizwe Combined School | Ndlambe LM | Kenton On Sea | MEC Adopted | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Mzingisi Primary School | Kouga LM | Humansdorp | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Archie Mbolekwa Primary | Makan LM | Makhanda | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Fikizolo Primary School | Makan LM | Makhanda | Agro-Eco School | 29 | 11240.4 | 4694.52 | 26943.9 | 3768.84 | 1586.88 | 48234.54
14 | Kutlhiso Daniels Secondary Schl | Makan LM | Makhanda | Agro-Eco School | 14 | 5426.4 | 2266.32 | 13007.4 | 1819.44 | 766.08 | 23285.64
15 | Ntsika Secondary School | Makan LM | Makhanda | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Samuel Ntlebi Primary School | Makan LM | Makhanda | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Samuel Ntsiko Public Primary | Makan LM | Makhanda | Agro-Eco School | 10 | 3876 | 1618.8 | 9291 | 1299.6 | 547.2 | 16632.6
18 | Zuney Intermediate School | Ndlambe LM | Alexandria (Along R72 road) | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Ukhanyo Secondary School | Ndlambe LM | Alexandria (Nonkqubela) | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Klipfontein Primary School | Ndlambe LM | BushmansRiverMouth | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | A.V Bukani Primary School | Sundays Rive Valley | Addo | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Bhongweni primary school | Ndlambe LM | Alexandria (Nonkqubela) | Agro-Eco School | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTALS |  |  |  | 93 | 36046.8 | 15054.84 | 86406.3 | 12086.28 | 5088.96 | 154683.18

## Implements
ESTIMATED COSTS OF REQUESTED TOOLS/IMPLEMENTS
NO | SCHOOL NAME | LOCAL MUNICIPALITY | LOCALITY/AREA | CATERGORY / CLASSIFICATION | QTY's | Garden Spade |  | Fork Spade |  | Wheelbarrow |  | Watering Can (5L Plastic) |  | Hose Pipe (12 x 30m) |  | Steel Rake |  | Hand Hoe (60cm Woode Handle) |  | Seedling Trays (200 square cavity) |  | Total Costs | RWH (5000L Water Tanks & Gutters)
[5 empty] | 321.0037 | QTY | 227 | QTY | 350 | QTY | 1264 | QTY | 139 | QTY | 269.52 | QTY | 136.85 | QTY | 136.67 | QTY | 44.99 | (Rands) | QTY | 18768.8246
1 | Msobomvu Full Service School | Blue Crane Route | Cookhouse | MEC Adopted | 6 | 3 | 681 | 3 | 1050 | 2 | 2528 | 3 | 417 | 2 | 539.04 | 3 | 410.55 |  | 0 |  | 0 | 5625.59 |  | 0
2 | Johnson Nqonqoza Senior Secondary | Blue Crane Route | Somerset East | MEC Adopted | 5 | 5 | 1135 | 5 | 1750 | 1 | 1264 |  | 0 | 2 | 539.04 | 3 | 410.55 | 3 | 410.01 |  | 0 | 5508.6 | 2 | 37537.6491
3 | Coldstream PS | Koukamma LM | Coldstream | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 | 2 | 37537.6491
4 | Gustav PS | Koukamma LM | Eersterivier | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 |  | 0
5 | Joubertina Sec. | Koukamma LM | Joubertina | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 | 2 | 37537.6491
6 | Iqhayiya Lethu S.S. | Koukamma LM | Kareedouw | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 | 3 | 56306.4736
7 | Louterwater PS | Koukamma LM | Louterwater | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 |  | 0
8 | Misgund PS | Koukamma LM | Misgund | MEC Adopted | 4 | 6 | 1362 | 6 | 2100 | 2 | 2528 | 6 | 834 |  | 0 |  | 0 | 2 | 273.34 | 6 | 269.94 | 7367.28 |  | 0
9 | Nombulelo Senior Secondary School | Makan LM | Makhanda | MEC Adopted | 4 | 5 | 1135 | 5 | 1750 | 1 | 1264 |  | 0 | 4 | 1078.08 |  | 0 |  | 0 |  | 0 | 5227.08 | 2 | 37537.6491
10 | Ikamvalesizwe Combined School | Ndlambe LM | Kenton On Sea | MEC Adopted | 4 | 15 | 3405 | 15 | 5250 | 3 | 3792 | 15 | 2085 |  | 0 |  | 0 | 15 | 2050.05 | 6 | 269.94 | 16851.99 | 4 | 75075.2982
11 | Mzingisi Primary School | Kouga LM | Humansdorp | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 5 | 1347.6 | 3 | 410.55 |  | 0 |  | 0 | 9130.15 |  | 0
12 | Archie Mbolekwa Primary | Makan LM | Makhanda | Agro-Eco School | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
13 | Fikizolo Primary School | Makan LM | Makhanda | Agro-Eco School | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
14 | Kutlhiso Daniels Secondary school | Makan LM | Makhanda | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 2 | 539.04 | 3 | 410.55 |  | 0 |  | 0 | 8321.59 | 2 | 37537.6491
15 | Ntsika Secondary School | Makan LM | Makhanda | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 5 | 1347.6 | 3 | 410.55 |  | 0 |  | 0 | 9130.15 |  | 0
16 | Samuel Ntlebi Primary School | Makan LM | Makhanda | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 2 | 539.04 | 3 | 410.55 |  | 0 |  | 0 | 8321.59 | 1 | 18768.8246
17 | Samuel Ntsiko Public Primary | Makan LM | Makhanda | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 3 | 808.56 | 3 | 410.55 |  | 0 |  | 0 | 8591.11 | 2 | 37537.6491
18 | Zuney Intermediate School | Ndlambe LM | Alexandria (Along R72 road) | Agro-Eco School | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
19 | Ukhanyo Secondary School | Ndlambe LM | Alexandria (Nonkqubela loc.) | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 3 | 808.56 | 3 | 410.55 |  | 0 |  | 0 | 8591.11 | 2 | 37537.6491
20 | Klipfontein Primary School | Ndlambe LM | BushmansRiverMouth | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 3 | 808.56 | 3 | 410.55 |  | 0 |  | 0 | 8591.11 | 2 | 37537.6491
21 | A.V Bukani Primary School | Sundays Rive Valley | Addo | Agro-Eco School | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0
22 | Bhongweni primary school | Ndlambe LM | Alexandria (Nonkqubela loc.) | Agro-Eco School | 6 | 5 | 1135 | 5 | 1750 | 3 | 3792 | 5 | 695 | 3 | 808.56 | 3 | 410.55 |  | 0 |  | 0 | 8591.11 |  | 0
| TOTALS |  |  |  | 91 | 104 | 23608 | 104 | 36400 | 43 | 54352 | 94 | 13066 | 34 | 9163.68 | 30 | 4105.5 | 30 | 4100.1 | 42 | 1889.58 | 146684.86 | 24 | 450451.7892

## Inputs-Seeds
|  |  | 500 | 325
|  |  | 100 | x |  |  | ESTIMATED COSTS OF REQUIRED SEEDS (Standard pakect of) | [7 empty] | 500 | g
NO | SCHOOL NAME | LOCAL | LOCALITY/AREA | CATERGORY / | QTY's | Beetroot |  | Butternut |  | Green Pepper |  | Onion |  | Spinach |  | Compost (20kg bag) |  | Total Costs
|  | MUNICIPALITY |  | CLASSIFICATION | 725.94 | QTY | 325 | QTY | 1130 | QTY | 1972.68 | QTY | 642.86 | QTY | 262.5 | QTY | 22.6 | (Rands)
1 | Msobomvu Full Service School | Blue Crane Route | Cookhouse | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
2 | Johnson Nqonqoza Senior Secondary | Blue Crane Route | Somerset East | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
3 | Coldstream PS | Koukamma LM | Coldstream | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
4 | Gustav PS | Koukamma LM | Eersterivier | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
5 | Joubertina Sec. | Koukamma LM | Joubertina | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
6 | Iqhayiya Lethu S.S. | Koukamma LM | Kareedouw | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
7 | Louterwater PS | Koukamma LM | Louterwater | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
8 | Misgund PS | Koukamma LM | Misgund | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
9 | Nombulelo Senior Secondary School | Makan LM | Makhanda | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
10 | Ikamvalesizwe Combined School | Ndlambe LM | Kenton On Sea | MEC Adopted | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
11 | Mzingisi Primary School | Kouga LM | Humansdorp | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
12 | Archie Mbolekwa Primary | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
13 | Fikizolo Primary School | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
14 | Kutlhiso Daniels Secondary school | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
15 | Ntsika Secondary School | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
16 | Samuel Ntlebi Primary School | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
17 | Samuel Ntsiko Public Primary | Makan LM | Makhanda | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
18 | Zuney Intermediate School | Ndlambe LM | Alexandria (Along R72 road) | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
19 | Ukhanyo Secondary School | Ndlambe LM | Alexandria (Nonkqubela loc.) | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
20 | Klipfontein Primary School | Ndlambe LM | BushmansRiverMouth | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
21 | A.V Bukani Primary School | Sundays Rive Valley | Addo | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
22 | Bhongweni primary school | Ndlambe LM | Alexandria (Nonkqubela location) | Agro-Eco School | 6 | 1 | 325 | 1 | 1130 | 1 | 1972.68 | 1 | 642.86 | 1 | 262.5 | 10 | 226 | 4559.04
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
| TOTALS |  |  |  | 132 |  | 7150 |  | 24860 |  | 43398.96 |  | 14142.92 |  | 5775 |  | 4972 | 100298.88

## RWH
BILL OF QUANTITIES - SUPPLY,DELIVERY AND INSTALLATION OF WATER HARVESTING EQUIPMENT AND MATERIAL FOR JUNIOR LANDCARE
ITEM NO | PAYMENT CLAUSE | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
A | PS 3 | CONTRACTOR'S ESTABLISHMENT ON SITE AND GENERAL OBLIGATIONS
The contractor's general obligations:
A1 |  | Fixed obligations | Lump sum | 1 | 1000 | 1000
A2 |  | Value-related obligations | Lump sum | 1 | 500 | 500
A3 |  | Time-related obligations | Month | 1 | 800 | 800
CARRIED FORWARD TO SUMMARY : | [5 empty] | 2300
B |  | SUPPLY,DELIVERY AND INSTALLATION OF WATER HARVESTING EQUIPMENT AND MATERIAL FOR JUNIOR LAND CARE( AGRO- ECO SCHOOL PROGRAMME)
B1 |  | NAME OF SCHOOL
B1.1 | PPS | Site preparation
B1.1.1 |  | Demolish the existing school apron only on the proposed area of the water tank stand | m² | 6.25 | 320 | 2000
B1.2 | PPS | Harvesting Equipment and Material
B1.2.1 |  | Supply, deliver and install Water Tank (5000L) | Each | 1 | 5323.54 | 5323.54
B1.2.2 |  | Water Tank Stand complete with anchors as per detailed drawing.The existing 5000L water tank stand must be installed and placed on the proposed water tank and anchored. | Each | 1 | 1500 | 1500
B1.2.3 |  | Supply,deliver and connect 2 down pipes complete with connectors, brackets and all necessary fittings, 2 taps must be installed | Each | 1 | 1000 | 1000
B1.2.4 |  | Replace Gutters (24m) : PVC Half Round | 6m | 6 | 320 | 1920
B1.2.5 |  | Water Pump - TRADEPOWER Water Pump with Tank Connector Kit (0.5hp Auto Switch) | Each |  | 3850 | 0
|  | CARRIED FORWARD TO TOTAL |  |  |  | 11743.54
C |  | HEALTH AND SAFTY REGULATIONS
C1 |  | The contractor's general obligations: | Lump sum | 1 | 1500 | 1500
CARRIED FORWARD TO SUMMARY : | [5 empty] | 1500
D |  | SUMMARY OF SECTIONS
1 |  | SITE ESTABLISHMENT |  |  |  | 2300
2 |  | SUPPY & INSTALLATION |  |  |  | 11743.54
3 |  | HEALTH &SAFETY |  |  |  | 1500
SUBTOTAL | [5 empty] | 15543.54
4 |  | Contingencies (5%) | 5% |  |  | 777.177
SUBTOTAL | [5 empty] | 16320.717
5 |  | VAT (15%) | 15% |  |  | 2448.1076
TOTAL | [5 empty] | 18768.8246