## Sheet1
TASK | Start date | End date | Actual Dates | Total | % complete | Resource | Test results | Comments | Task Completed | Comments
Re-design homepage | 2020-10-01 | 2020-10-29 |  | 21 days | 0% | Ntombi Mtetwa
TOP GLOBAL MENU | 2020-10-01 | 2020-10-02 |  | 2 days | 0% | Ntombi Mtetwa
Add Services | 2020-10-01 | 2020-10-01 |  |  | 0% |  | pass
Add Parliamentary Matters | 2020-10-01 | 2020-10-01 |  |  | 0% |  | pass
Sub menu : Question & Answers | 2020-10-01 | 2020-10-01 |  |  | 0% |  | Pass
Sub menu: Presentations | 2020-10-01 | 2020-10-01 |  |  | 0% |  | Fail | Page not found. | Done | Page is created as per the request
Move Speeches to Newsroom | 2020-10-02 | 2020-10-02 |  |  | 0% |  | Pass | Page not found. Speehes page | ???? | Speeches page is already moved to Newsroom as per the request
Submenu 1: Media Invites | 2020-10-02 | 2020-10-02 |  |  | 0% |  | Fail | There is minister, deputy minister and other speeches | ??? | Afika to elaborate his test decision
Submenu 2: Speeches | 2020-10-02 | 2020-10-02 |  |  | 0% |  | Fail | There is minister, deputy minister and other speeches | ??? | Afika to elaborate his test decision
INFORMATION CORNER | 2020-10-05 | 2020-10-07 |  | 3 days | 0% | Ntombi Mtetwa
Add Statistics | 2020-10-05 | 2020-10-05 |  |  | 0% |  | Pass
Add FAQ | 2020-10-06 | 2020-10-06 |  |  | 0% |  | Pass
Add Events | 06 Oct | 2020-10-06 |  |  | 0% |  | Pass
Move Agriculture Colleges to Careers | 2020-10-07 | 07 Oct |  |  | 0% |  | Fail | colleges not on Careers | Done | DALRRD Title added and Agriculture Colleges is added under the title as per the meeting discussion
Move Producer Farm Registry to Current Initiatives | 07 Oct | 07 Oct |  |  | 0% |  | Pass | should it be a document or a page?
QUICK LINKS | 2020-10-08 | 2020-10-09 |  | 2 days | 0% | Ntombi Mtetwa
Add PSSC’s addresses after Prov. Websites | 2020-10-08 | 2020-10-08 |  |  | 0% |  | Pass | But its before province website | Done | Reordered the links as per the requirements
Add Non-gov. Stakeholders | 2020-10-08 | 2020-10-08 |  |  | 0% |  | Pass
Move Certificate for SMS entry to Careers | 09 Oct | 09 Oct |  |  | 0% |  | Pass
Move email Access to footer next to site map (was kept as is, not moved) | 09 Oct | 09 Oct |  |  | 0% |  | No change
INTERNAL ENTITIES/PROGRAMMES/PROJECTS (Add strip below Outbreaks) | 2020-10-12 | 2020-10-16 |  | 5 days | 0% | Ntombi Mtetwa
Restitution – Deeds –– NGMS/NGI (background - coded brown) | 12 Oct | 14 Oct |  |  | 0% |  | Pass
SASDI - CGS- NARYSEC- (colour approved coded brown) | 15 Oct | 16 Oct |  |  | 0% |  | Pass
CURRENT INTIATIVES (Auto scroll bar) – (link and underline styling for list) | 2020-10-19 | 2020-10-20 |  | 2 days | 0% | Ntombi Mtetwa
Farmer Registry | 2020-10-19 | 2020-10-19 |  |  | 0% |  | Pass
COVID-109 Agriculture Disaster Support Fund | 2020-10-19 | 2020-10-19 |  |  | 0% |  |  | the page is not accessible. Permission issues | ???? | This was done by my collegaue on agreement with Nwabisa during the intitial project for COVID-19 Support Funds
Agric Master Plan and Poultry | 2020-10-20 | 2020-10-20 |  |  | 0% |  | Pass
Karoo Regional Spatial Development Framework | 2020-10-20 | 2020-10-20 |  |  | 0% |  | Pass
SPECIAL FEATURES (Auto scroll bar) (Image and link styling for list) | 2020-10-21 | 2020-10-22 |  | 2 days | 0% | Ntombi Mtetwa
Land Bank | 21 Oct | 21 Oct |  |  | 100% |  | Pass
DALRRD International | 2020-10-22 | 2020-10-22 |  |  | 100% |  | Pass
Legal Matters | 2020-10-22 | 2020-10-22 |  |  | 100% |  | Pass
COVID-19 | 2020-10-23 | 2020-10-23 |  | 1 day | 0% | Ntombi Mtetwa
Add COVID-19 Image with link under DG Shabane | 23 Oct | 2020-10-23 |  |  | 0% |  | the image was moved to intergovernmental/supporting strip
EVICTIONS | 2020-10-26 | 2020-10-26 | 07-14 December 2020 | 1 day | 0% | Ntombi Mtetwa
Add IMAGE WITH “ARE YOU EVICTED?” next to Gallery | 26 Oct | 26 Oct | 07-14 December 2020 |  | 0% |  | Fail | The image is there, but it does not provide any info for someone who is evicted. I suggest that the image should click link on DRDLR site or should have a link to a page which will provide more info. Same goes for NDP or stay safe | Done | The link to the is image is added and directs to the page
FOOTER | 2020-10-27 | 2020-10-27 |  | 1 day | 0% | Ntombi Mtetwa
Add Email Access next to site map (was not moved kept as it was) | 2020-10-27 | 2020-10-27 |  |  | 0% |  |  | its still under quick links
Change background colour to green | 2020-11-30 | 2020-12-01 | 2020-11-30 |  | 100% |  | Pass
Talk to the Department (chat app) further investigation by OCIO | 2020-10-28 | 2020-10-29 |  | 2 days | 0% | Afika Ngcwabe | not implemented, the Chat requires further investigations by CIO. If FAQ & answers can be sourced to capacitate the app. Is there human resource to manage the chats. | To investigate the possble solution
1. Special Features
Branches can move under About Us. Shouldn’t move - will take longer to get to the info currently working in Phase 2. Leave as is | [7 empty] | Remained on the top menu
Restitution should be elevated (as well as Deeds, NGMS). Already available on the home page (should they be moved to the global menu??) will end up having a cluttered global menu. Leave as is, Create colourful block, create a block on right side. | [6 empty] | Done
Evictions information should be reflected. | [6 empty] | Fail | There is just an image | Done | Link added to the image.
DALRRDs International: International Engagements – MOU and trade agreements, Agri Attaches. | [6 empty] | Done | Page can't be reached | ???? | Page is already thhere, unless if I'm missing something
Current initiatives: Farmer Registers. Move it from Info Corner to special features and replace it with Statistics. | [6 empty] | Done | This site can't be reached | ???? | I guess Afika didn’t understand the requirement, Move Producer Farm Registry to Current Initiatives is done already
Legal Matters: Bills for public comments, court cases, notices, legislation. Rename public hearings to public comments | [6 empty] | done
2. Items to be visible:
Links to the Land Bank (to create a link, be added with icon, next to public entities) | [6 empty] | done
and other entities. Move to new space called Intergovernmental – identify the new space on the home page. Delete
Services offered by the Department. Move to global menu | [6 empty] | done
From DDG comments – Statistics. Move to Info corner. Create a page that refers to all available stats, since statistics are available need to have a link to stats under publications. | [6 empty] | done
Parliamentary Matters – (Q&A, presentations, etc). Under Parliamentary Updates will have submenu Q&A, presentations etc. Move to Global Menu. | [6 empty] | done
3. Look at Environmental, Forestry and Fisheries, NAMC websites as a benchmark/guidance. Have referenced/checked the recommended sites. (Done)
4. Talk to the Department (chat app) – OCIO to assist/advice on platforms to use for communication. IT to help explore the provision of platform. (Info forum to give content & maintain with responses). Auto response must be created, when form has been submitted it should go straight to call centre, presidential hotline & lodge as query) | [6 empty] | Planned to be implemented
5. Interactions with provincial departments, DALRRD PSSCs, Other related links (External non-governmental stakeholders)
6. Information Gathering: Mathapelo Please add info..Convene forum to look at the information gap.(done by KIM not Mathapelo)
7. Way forward
· Convene site mapping meeting with the implementation team on Wednesday 23/09/2020 to discuss readjustment of the structure.done
· Design amended layout (on Thursday, then discuss with IT team on Friday, 25 Sep.)
· Determine timelines for adjustment. (Plan to be compiled)
· Implement accordingly
· After the readjustment, present to new structure to the Minister, go live and continue with content migration
8. Proposals
Move Events and Email to the footer.
Move FAQ to Quick links. | [7 empty] | Are on Information Corner
Move Speeches to Newsroom. Media Invites should be the first submenu followed by Speeches. | [6 empty] | done
Move Parliamentary matters Q& A from Newsroom to Parliamentary Updates. | [6 empty] | done
Add PSSC’s addresses on Quick links under Provincial Websites. | [6 empty] | done | need to re-arrange | Done | As per the request, it is done
Certificate for SMS training (NSG) and Agric Colleges move it to Careers (internal & external). | [6 empty] | done partly | Agriculture Colleges need to be added to Careers
Put Special Features under Outbreaks and Public Entities. The space under DG can be used for new topic Intergovernmental. | [9 empty] | Afika to elaborate his testing decision, I don’t understand.
The logo does not appear or load on other menu items such as “About Us”, Branches sub-menu, newsroom sub-menu, publications sub-menu | [9 empty] | It is attended to, all pages and subpages reflects the DALRRD logo.
The multi-media issue not displaying on the home page does not look good. Need to check the url used in the webpart if it is not broken. The youtube opens when click watch more.